## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Produce draft vision | 1 | 2 | Closed | 1 |  | 0 | 18
Support basic order entry process | 1 | 8 | Closed | 1 | Lisa | 0 | 56 | <UC:Inventory Control>
Prototype UI |  |  | Closed | 1 | Ann | 0 | 5 | <User Interface Guidelines.pdf>
Do the design |  |  | Closed | 1 | Lisa, Ann, Johan | 0 | 8
Implement and test server portion |  |  | Closed | 1 | Ann | 0 | 23
Implement and test client portion |  |  | Closed | 1 | Johan | 0 | 14
Update end user documentation |  |  | Closed | 1 | Lisa | 0 | 6
Finalize the Vision | 1 | 1 | Resolved | 2 | Peter | 2 | 12 | <Vision.doc>
Complete the order entry process | 2 | 8 | Verified | 2 | Johan | 2 | 66 | <UC: Order Entry>
Confirmation page displays incorrect date | 2 |  | Closed | 2 | Johan | 0 | 23
Sort orders by name | 2 |  | Closed | 2 | Ann | 0 | 18
Sort orders by order number | 3 |  | Verified | 2 | Johan | 2 | 25
Play happy sound when order is complete | 5 |  | Closed (out of scope)
Support simple inventory control | 2 | 8 | Assigned | 3 | Lisa | 70 | 0 | <UC:Inventory Control>
Prototype UI |  |  | Resolved | 2 | Ann | 10 | 0 | <User Interface Guidelines.pdf>
Do the design |  |  | Assigned | 3 | Lisa, Ann, Johan | 12 | 0
Implement and test server portion |  |  | Assigned | 3 | Ann | 14 | 0
Implement and test client portion |  |  | Assigned | 3 | Johan | 28 | 0
Update end user documentation |  |  | New | 3 | Lisa | 6 | 0
Allow disconnected use | 5 | 100 | New |  |  |  |  | <Long term vision.doc>
Produce demo for Supply Chain 2007 Conference | 3 | 5 | Assigned | 3 | Ann | 18 | 2
Edit end user documentation | 2 | 5 | Assigned | 3 | Lisa | 65 | 11
Edit install manual | 2 | 1 | Assigned | 3 | Lisa | 5 | 4
Edit release notes | 2 | 1 | Assigned | 3 | Johan | 4 | 4
Edit online help | 3 | 2 | Assigned | 3 | Ann | 22 | 3
Edit training course | 4 | 3 | Assigned | 4 |  | 34 | 0 | <Supply Chain 101.ppt>
Note on A1: Example introduction: A red triangle in upper right corner of cell means that you can right click and view comment, which provides explanatory text. This example shows a small Work Items List for a team that just finished iteration 2, has planned iteration 3, and have done a few hours of work on iteration 3. A real Work Items List would have many more entries. Columns in light blue color (E-H) are typically used when a Work Item is assigned to an iteration. The other columns are typically used regardless of whether the work item is assigned to an iteration or not.
Note on A4: You often divide a scenario into smaller functional tasks that enables you to more easily track progress.
Note on A11: When you have more complete use cases, versus incmplete scenarios, you can more easily divide the remainder of the use case into additional capabilities, each providing end user value, instead of doing a functional decomposition into subtasks, where the subtasks do not add value by themselves.
Note on B4: Since you want to make sure that you deliver something of value, you need to do all of the child tasks for this work item. If that would not fit within an iteration, you should narrow the scope to include less functionality in this iteration (and moving the rest of the work to future iterations). You will still do design, implementation and testing of a complete set of functionality.
Note on C5: Typically, you do not do size estimates for child work items that are not meaningful deliverables by themselves. You break down to these small work items to enable effective planning and tracking, but they are typically not prioritized and size estimated independently.
Note on C22: Since the Work Item is huge, the team put down 100 as estimate. It does not matter if the correct number is 70 or 150, since it is still a low priority. In the future, as the priority is higher, the team needs to improve their estimate, and break it down into more manageable child-work items that can be prioritized independently.
Note on D3: The states used in this example are the same as recommended by Eclipse for their bugs; New, Assigned, Resolved, Verified, and Closed. You may need to define your own states.
Note on D10: This is an example of a work item where all work was not completed within an iteration as planned. A couple of hours is left to be completed in iteration 3.
Note on D14: This is an example of a work item where all work was not completed within an iteration as planned. A couple of hours is left to be completed in iteration 3. This also prevents the parent work item to reach state Closed.
Note on D15: This work item is out of scope for the project. Some teams have an iteration "100" that is used to denote that it is for a fictive future iteration.
Note on F28: Since planning for iteration 4 has not yet started, nobody is assigned to this task yet.