## Iteration Burndown Chart
Iteration Burndown: Iteration 3
<<See comments for explanation of why the estimated effort looks as is does for this team. If you do not see the comments, hold your mouse over cells with a red triangle in upper right corner.>>
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Effort let (hours) | 480 | 450 | 416 | 560 | 534 | 508 | 468 | 434 | 532 | 512 | 482 | 332 | 297 | 260 | 222 | 181 | 148 | 104 | 62 | 25
Change relative to previous week |  | 30 | 34 | -144 | 26 | 26 | 40 | 34 | -98 | 20 | 30 | 150 | 35 | 37 | 38 | 41 | 33 | 44 | 42 | 37
Note on B4: This example is for a 6-person team doing a 4-week iteration (20 working days). Since the team knows that they on average get 5 hours per day of real work done and that they typically underestimate the effort to complete a task by 20%, they only took on 4 hours of estimated work per person per day, or 6 people x 4 weeks x 5 days/week x 4 hours/day = 480 hours.
Note on D4: With 6 people in the project, you would expect roughly 30 hours (6 x 5 hours) of real work to be done each day, so things look like expected so far.
Note on E4: The team got together and made sure that all estimates were realistic. Based on what team members had learnt in the first 3 days, estimates were primarily increased. This is not yet alarming, hopefully the new estimates are more realistic, and they can still complete everything, since what they had accomodated for a 20% underestimate in their original calculation.
Note on I4: Looks as if project is on track again.
Note on J4: The team realized that a scenario is much more difficult to implement than they expected, and they changed their estimate, it is now looking tough to get the work done on time. They need to look into de-scoping if nothing changes.
Note on M4: The team agreed with stakeholders to de-scope some of the work for the iteration so they can complete on time.
Note on U4: The team completed all work items but 2. They decided to end the current iteration on time and carry over those two work items to the next iteration. The team will use the fact that they underestimated the work to adjust their estimates for the next iteration.