Genesis Supply Chain Project

Iteration Plan - 3

# Key Milestones

| Milestone | Date |
| --- | --- |
| Iteration Start | 7/1 |
| EXPOWEST Demo | 7/24 |
| Iteration Stop | 7/31 |

# High-level Objectives

- Address usability issues raised by the Order Management department.

- Deliver key scenarios showcasing meaningful integration with SAP.

- Enable early adopters to download and install new builds without requiring constant handholding by the development team

- Deliver a technical demo at EXPOWEST

# Work Item Assignments

| Name / Description | Priority | Size estimate (Points) | Assig-ned To | Effort estimate (hours) |
| --- | --- | --- | --- | --- |
| Support simple inventory control | 2 | 8 | Lisa | 70 |
| Do the design |  |  | Lisa, Ann, Johan | 12 |
| Implement and test server portion |  |  | Ann | 14 |
| Implement and test client portion |  |  | Johan | 28 |
| Update end user documentation |  |  | Lisa | 6 |
| Produce demo for Supply Chain 2007 Conference | 3 | 5 | Ann | 18 |
| Edit end user documentation | 2 | 5 | Lisa | 65 |
| Edit install manual | 2 | 1 | Lisa | 5 |
| Edit release notes | 2 | 1 | Johan | 4 |
| Edit online help | 3 | 2 | Ann | 22 |

# Evaluation Criteria

- 97% of system-level test cases passed.

- Scenarios for Simple inventory control properly tested and demoed to key stakeholders

- End user documentation get favorable acceptance by end users

- Walkthrough of iteration build with Order Management and Financial Services departments are well received.

- Favorable response to technical demo at Supply Chain 2007 Conference.